## Lookups
Priority | Status | Issue Category | Department | Assignment Type | Assignee
High | New | Brakes | Transit Operations | Internal Technician | Alex M.
Medium | Assigned | Engine | Waste & Recycling | External Vendor | Prairie Fleet Services
Low | In Progress | Electrical | Water Services |  | Jordan K.
| Pending Approval | Tires | Roads |  | Westside Auto
| Completed | HVAC | Parks |  | Sam R.
| Closed | Body / Exterior | Fleet Services |  | Calgary Mobile Repair
Preventive Maintenance
Other

## Pivot_Status
Row Labels | Count of Work Order ID
Assigned | 2
Closed | 1
Completed | 1
In Progress | 5
New | 3
Pending Approval | 1
Grand Total | 13

## Work Orders by Department and P
Count of Work Order ID | Column Labels
Row Labels | High | Low | Medium | Grand Total
Fleet Services |  |  | 1 | 1
Parks |  | 1 |  | 1
Roads |  |  | 2 | 2
Transit Operations | 1 | 2 | 1 | 4
Waste & Recycling | 1 | 1 | 1 | 3
Water Services | 1 |  | 1 | 2
Grand Total | 3 | 4 | 6 | 13

## Assignee_Lookup
Assignee | Type | Team / Role | Contact Category
Alex M. | Internal | Fleet Technician | Internal
Jordan K. | Internal | Fleet Technician | Internal
Sam R. | Internal | Fleet Technician | Internal
Prairie Fleet Services | Vendor | External Repair Vendor | External
Westside Auto | Vendor | External Repair Vendor | External
Calgary Mobile Repair | Vendor | Mobile Repair Vendor | External

## Estimated Cost by Issue Categor
Row Labels | Sum of Estimated Cost
Body / Exterior | 950
Brakes | 850
Electrical | 2890
Engine | 5300
HVAC | 1450
Preventive Maintenance | 1200
Tires | 1120
Grand Total | 13760

## Cleaned_Work_Orders
Work Order ID | Vehicle / Equipment ID | Department | Issue Category | Issue Description | Priority | Reported Date | Assigned To | Assignee Type | Assignment Type | Status | Estimated Cost | Approval Required | Approval Status | Due Date | Completion Date | Ageing (Days) | Overdue? | Notes | Action Required
WO-1001 | BUS-214 | Transit Operations | Brakes | Brake warning light reported during pre-trip inspection | High | 2026-10-01 | Alex M. | Internal | Internal Technician | In Progress | 850 | No | Not Required | 2026-10-03 |  | 22 | Yes | Vehicle held for inspection | No Approval Action
WO-1002 | TRK-087 | Waste & Recycling | Engine | Engine losing power under load | High | 2026-09-28 | Prairie Fleet Services | Vendor | External Vendor | Pending Approval | 4200 | Yes | Pending | 2026-10-02 |  | 25 | Yes | Vendor estimate received | Approval Follow-up
WO-1003 | VAN-055 | Water Services | Tires | Front tires below tread standard | Medium | 2026-10-02 | Jordan K. | Internal | Internal Technician | Assigned | 620 | No | Not Required | 2026-10-08 |  | 21 | Yes | Replacement tires available | No Approval Action
WO-1004 | PLOW-018 | Roads | Electrical | Beacon light intermittent | Medium | 2026-09-30 | Westside Auto | Vendor | External Vendor | Completed | 540 | No | Not Required | 2026-10-05 | 2026-10-04 | 4 | No | Wiring connector replaced | No Approval Action
WO-1005 | MOWER-31 | Parks | Preventive Maintenance | Seasonal maintenance and inspection | Low | 2026-10-03 | Sam R. | Internal | Internal Technician | New | 300 | No | Not Required | 2026-10-12 |  | 20 | Yes | Scheduled service | No Approval Action
WO-1006 | SUV-122 | Fleet Services | HVAC | Cabin heater not reaching temperature | Medium | 2026-09-25 | Calgary Mobile Repair | Vendor | External Vendor | In Progress | 1450 | Yes | Approved | 2026-10-01 |  | 28 | Yes | Parts ordered | No Approval Action
WO-1007 | BUS-331 | Transit Operations | Body / Exterior | Passenger door panel damaged | Low | 2026-10-05 | Alex M. | Internal | Internal Technician | New | 950 | No | Not Required | 2026-10-15 |  | 18 | Yes | Awaiting inspection | No Approval Action
WO-1008 | TRK-144 | Waste & Recycling | Electrical | Reverse camera not functioning | Medium | 2026-09-27 | Prairie Fleet Services | Vendor | External Vendor | Assigned | 1800 | Yes | Approved | 2026-10-04 |  | 26 | Yes | Appointment booked | No Approval Action
WO-1009 | VAN-072 | Water Services | Engine | Check-engine light and rough idle | High | 2026-10-06 | Jordan K. | Internal | Internal Technician | In Progress | 1100 | No | Not Required | 2026-10-07 |  | 17 | Yes | Diagnostics underway | No Approval Action
WO-1010 | PLOW-041 | Roads | Preventive Maintenance | Pre-winter inspection | Medium | 2026-10-01 | Westside Auto | Vendor | External Vendor | Closed | 900 | No | Not Required | 2026-10-06 | 2026-10-05 | 4 | No | Inspection complete | No Approval Action
WO-QA-1011 | BUS-QA-01 | Transit Operations | Electrical | QA: future due date and approval pending | Medium | 2026-10-23 | Alex M. | Internal | Internal Technician | In Progress | 350 | Yes | Pending | 2026-11-09 |  | 0 | No | Synthetic QA edge case | Approval Follow-up
WO-QA-1012 | TRK-QA-02 | Waste & Recycling | Tires | QA: new record beyond original cost range | Low | 2026-10-23 | Alex M. | Internal | Internal Technician | New | 500 | No | Not Required | 2026-11-09 |  | 0 | No | Synthetic QA cost expansion | No Approval Action
WO-QA-1013 | BUS-QA-03 | Transit Operations | Electrical | QA: pending status without approval required | Low | 2026-10-23 | Alex M. | Internal | Internal Technician | In Progress | 200 | No | Pending | 2026-11-09 |  | 0 | No | Synthetic QA approval definition edge case | No Approval Action

## Work Orders
Work Order ID | Vehicle / Equipment ID | Department | Issue Category | Issue Description | Priority | Reported Date | Assigned To | Assignee Type | Assignment Type | Status | Estimated Cost | Approval Required | Approval Status | Due Date | Completion Date | Ageing (Days) | Overdue? | Notes | Action Required
WO-1001 | BUS-214 | Transit Operations | Brakes | Brake warning light reported during pre-trip inspection | High | 2026-10-01 | Alex M. | Internal | Internal Technician | In Progress | 850 | No | Not Required | 2026-10-03 |  | 24 | Yes | Vehicle held for inspection | No Approval Action
WO-1002 | TRK-087 | Waste & Recycling | Engine | Engine losing power under load | High | 2026-09-28 | Prairie Fleet Services | Vendor | External Vendor | Pending Approval | 4200 | Yes | Pending | 2026-10-02 |  | 27 | Yes | Vendor estimate received | Approval Follow-up
WO-1003 | VAN-055 | Water Services | Tires | Front tires below tread standard | Medium | 2026-10-02 | Jordan K. | Internal | Internal Technician | Assigned | 620 | No | Not Required | 2026-10-08 |  | 23 | Yes | Replacement tires available | No Approval Action
WO-1004 | PLOW-018 | Roads | Electrical | Beacon light intermittent | Medium | 2026-09-30 | Westside Auto | Vendor | External Vendor | Completed | 540 | No | Not Required | 2026-10-05 | 2026-10-04 | 4 | No | Wiring connector replaced | No Approval Action
WO-1005 | MOWER-31 | Parks | Preventive Maintenance | Seasonal maintenance and inspection | Low | 2026-10-03 | Sam R. | Internal | Internal Technician | New | 300 | No | Not Required | 2026-10-12 |  | 22 | Yes | Scheduled service | No Approval Action
WO-1006 | SUV-122 | Fleet Services | HVAC | Cabin heater not reaching temperature | Medium | 2026-09-25 | Calgary Mobile Repair | Vendor | External Vendor | In Progress | 1450 | Yes | Approved | 2026-10-01 |  | 30 | Yes | Parts ordered | No Approval Action
WO-1007 | BUS-331 | Transit Operations | Body / Exterior | Passenger door panel damaged | Low | 2026-10-05 | Alex M. | Internal | Internal Technician | New | 950 | No | Not Required | 2026-10-15 |  | 20 | Yes | Awaiting inspection | No Approval Action
WO-1008 | TRK-144 | Waste & Recycling | Electrical | Reverse camera not functioning | Medium | 2026-09-27 | Prairie Fleet Services | Vendor | External Vendor | Assigned | 1800 | Yes | Approved | 2026-10-04 |  | 28 | Yes | Appointment booked | No Approval Action
WO-1009 | VAN-072 | Water Services | Engine | Check-engine light and rough idle | High | 2026-10-06 | Jordan K. | Internal | Internal Technician | In Progress | 1100 | No | Not Required | 2026-10-07 |  | 19 | Yes | Diagnostics underway | No Approval Action
WO-1010 | PLOW-041 | Roads | Preventive Maintenance | Pre-winter inspection | Medium | 2026-10-01 | Westside Auto | Vendor | External Vendor | Closed | 900 | No | Not Required | 2026-10-06 | 2026-10-05 | 4 | No | Inspection complete | No Approval Action
WO-QA-1011 | BUS-QA-01 | Transit Operations | Electrical | QA: future due date and approval pending | Medium | 2026-10-23 | Alex M. | Internal | Internal Technician | In Progress | 350 | Yes | Pending | 2026-11-09 |  | 2 | No | Synthetic QA edge case | Approval Follow-up
WO-QA-1012 | TRK-QA-02 | Waste & Recycling | Tires | QA: new record beyond original cost range | Low | 2026-10-23 | Alex M. | Internal | Internal Technician | New | 500 | No | Not Required | 2026-11-09 |  | 2 | No | Synthetic QA cost expansion | No Approval Action
WO-QA-1013 | BUS-QA-03 | Transit Operations | Electrical | QA: pending status without approval required | Low | 2026-10-23 | Alex M. | Internal | Internal Technician | In Progress | 200 | No | Pending | 2026-11-09 |  | 2 | No | Synthetic QA approval definition edge case | No Approval Action
Formulas:
Ageing (Days) = IF([Completion Date]<>"",[Completion Date]-[Reported Date],TODAY()-[Reported Date])
Overdue? = IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed",[Status]<>"Closed"),"Yes","No")

## Summary
Fleet Maintenance ¦ Work Order Dashboard
Metric | Value | Status | Count
Total Work Orders | 13 | New | 3
Open Work Orders | 11 | Assigned | 2
High Priority | 3 | In Progress | 5
Overdue | 8 | Pending Approval | 1
Approvals Requiring Action | 2 | Completed | 1
Total Estimated Cost | 13760 | Closed | 1
Report Date | 2026-10-25
High Priority & Overdue | 3
Engine Repair Cost | 5300
High Priority Vendor Cost | 4200